## Test report
Project Name:
Developers:
Release:
Nr | User Story | Task description | Priority | Tested by | Comments | Status
The undersigned acknowledge and accept delivery of the work completed for this deliverable on behalf of the Organization I represent. My signature attests to my agreement that deliverable has been completed.
Name
Signature
Date

## Alfa Log
|  | Project Name: | ELITE HANDCRAFTS
|  | Developers: | 1)Rahul Rao Yenugula
2)Prashanth Reddy Bhagirathi
3)LEELA MADHAV SAJJA
4)SUSHMITHA PERAM
User stories log
Release | Nr | User Story | Description | Priority | Time (days) | Status
Alfa ICT1 5 weeks | 1) | HOME PAGE | User can view the description about Elite Handcrafts | 10 | 6 | in progress
| 2) | CONTACT PAGE | User can access List of sources that a customer can contact | 20 | 5
| 3) | OFFERS PAGE | Admin displays offers based on seasons, Festivals | 20 | 5
| 4) | PRODUCTS PAGE | User can view Categories & prices for products | 30 | 5
| 5) | LOCATIONS PAGE | User can view List of locations with maps api | 40 | 5
Beta ICT2 5 weeks |  | Bug fixes | Bug fixes performed on Products page and Offers Page | 20 | 4
| 1) | DATABASE | Admin stores the details of registered members | 20 | 5
| 2) | LOG IN PAGE | User can log in To view current promotions | 20 | 5
| 3) | SIGNUP | User can creat an account To become member in Elite Star Club | 20 | 4
| 4) | ELITE STAR CLUB | Loyal Customers receive vouchers and offers in Separate page | 30 | 5
| 5) | FRANCHISES ENQUIRY | Users can access Enquiry Form for franchise | 50 | 2
Final ICT2 5 weeks |  | Bug fixes | DEVELOPER PERFORMS FIXING BUGS FROM BETA RELEASE | 10 | 5
| 1) | PRODUCTS PAGE | Admin Updating products frequently | 10 | 6
| 2) | HOME PAGE | Developer Finalises the page layout | 20 | 5
| 3) | ELITE STAR CLUB | Developer improvise Layouts | 20 | 4
| 4) | DATABASE | Admin Updates database | 20 | 5

## Beta Log
Project Name:
Developers:
User stories log
Release | Nr | User Story | Description | Priority | Time (days) | Status
Alfa ICT1 5 weeks | 1 |  |  | 10 |  | completed
| 2 |  |  | 10 |  | completed
3
Beta ICT2 5 weeks |  | Bug fixes |  | 10 |  | in progress
|  |  |  | 10 |  | in progress
Final ICT2 5 weeks |  | Bug fixes

## Final Log
Project Name:
Developers:
User stories log
Release | Nr | User Story | Description | Priority | Time (days) | Status
Alfa ICT1 5 weeks | 1 |  |  | 10 |  | completed
| 2 |  |  | 10 |  | completed
3
Beta ICT2 5 weeks |  | Bug fixes |  | 10 |  | completed
|  |  |  | 10 |  | completed
Final ICT2 5 weeks |  | Bug fixes |  | 10 |  | in progress
|  |  |  | 10 |  | in progress